## Institutionalization
CARTA Institutionalizaion projects
No | Institution | Title of project | Strategies | Year of Award | 1st Project report date | 2nd Project report date | 3rd Project report date | 4th Project report date | 5th Report Date | 6th Report Date | Final Project Report Date | Anticipated End date (if extension) | Amount of grant in $ | Completion status | Actual Date of completion | Outcomes | Project lead | Project outcomes | Reporting date
1 | Makerere University | Strengthening capacity for doctoral training and supervision at Makerere University: a multidisciplinary doctoral students and supervisors’ mentorship approach. | Harmonizing of crosscutting content for the PhD curriculum; Harmonizing of Continued Professional Development (CPD) curriculum for PhD supervisors; Reviewing of graduate training policies and guidelines. | 2017-07-01 | 2018-07-01 | 2019-05-01 | 2019-12-01 | 2020-09-12 |  |  | 2021-01-02 | 2020-12-31 | 100000 | Completed | 2020-12-31 | Four (4) PhD cross-cutting courses and one (1) supervisors’ course were identified and agreed upon as compulsory courses for all PhD fellows, and would be run on a modular basis with each course offered each year or depending on demand. These courses were:Research Methods & Proposal Development,Qualitative Data Analysis, Interpretation and Presentation, Quantitative data analysis, interpretation and presentation and Scholarly Writing & Communication Skills . Training schedules for all the harmonized courses were developed. Development of harmonized content for face-to-face and online delivery of the following courses: Research Methods & Proposal Development, Qualitative Data Analysis, Interpretation and Presentation,Quantitative data analysis, interpretation and presentation and Scholarly Writing & Communication Skills. Development of harmonized content for face-to-face and online delivery of the Continued Professional Development for Doctoral Supervisors course completed. | Assoc. Professor David Okello Owiny
2 | Moi University | Improvement of Competencies and Completion Rates among Doctoral Fellows through Strengthening of Supervision, Mentorship d Integration of Courses | Strengthening supervisor training, supervision and mentorship process for graduate training at Moi University, Augmenting competencies of graduates by integrating and harmonizing relevant priority CARTA Joint Advanced Seminars (JASes) courses into existing graduate curricula, Institutionalizing best practices in research and grants management culture by enhancing capacity of academic and administrative staff delivery quality service and manage postgraduate training; and mobilization and management of research funds | 2019-12-01 | [7 empty] | 2020-11-30 | 15000 | Active |  | Customized and adopted supervisors’ training manual—adapted from the CARTA supervisors workshop manual—was developed and adopted to support graduate supervision. The first supervisors’ training was held in April 2021 and by July 2022, 335 supervisors of both masters and Phd students. Though gradual, there are changes in the supervisors attitude towards supervision after participating in the training. For example, some supervisors began reaching out to their supervisees, which did not happen before. As a result, delayed students, such as students who registered as far as 2010, had submitted their thesis for examination.had been trained. The training covered postgraduate supervision, mentorship of graduate faculty, and the examination process. Content from the training sessions was compiled into the manual to support continued learning. To strengthen graduate outcomes, aspects Joint Advanced Seminars (JASes) courses were integrated and harmonized into the existing graduate curriculum. research methodology curriculum, a mandatory course offered to all Masters and Ph.D. students in the School of Arts. This course has provided uniformity in research methodology as all masters and Ph.D. take this course. | Prof. Ann Nangulu
3 | Moi University | Infrastructural Project on Strengthening ad Refurbishing of CARTA Postgraduate Lab/Training space; and CARTA Committee Room at Moi University (at Main Campus at School of Arts and Social Sciences) ANDICT connectivity |  | 2020-02-28 | [7 empty] | 2020-09-30 | 20000 | Active |  | Moi University has computer lab for postgaduate students that was equped by CARTA the zoom licenses purchased for partner institutions to mitigate the effects of COVID-19 on University activities. At Moi, teaching, oral defense, and Board meetings continued to be held even during the pandemic. Participation in these events increased since they are virtual, and one can join from any location. | Prof. Christopher Odhiambo
4 | Obafemi Awolowo University | Intervention towards Strengthening Research Training in Obafemi Awolowo University (ItSTRETO) | Introduction of the Joint Seminars Series (JSS) and holding of Supervisors Retreats | 2017-07-01 | 2018-11-01 | 2019-04-01 | 2019-12-01 | 2020-06-01 | 2020-07-01 | 2020-10-20 | 2021-01-14 | 2020-12-31 | 99025 | Completed | 2020-12-31 | The development of the curriculum and teaching modules on critical thinking/conceptual skills building and literature for the four Joint Seminar Series , Holding of training sessions among the post-graduate students for each of the four JSS, Convening of three Supervisors’ Academic Retreat (SARs) , Convening of three Graduate Training Stakeholders’ Forum (GTSF), establishment of an e-library for postgraduate students, which was a decision emanating from the first GTSF of the ItSTRETO project. Approval of the periodic training for supervisors by the Business Committee of Senate (Still awaiting complete approvals from Senate). Adoption by the postgraduate college of the plagiarism test that was proposed through the ItSTRETO project as a criterion for subsequent postgraduate students at the entry level with evidence of certificate received. This was also approved by the Business Committee of Senate. The university-wide research method course (URM 901) successfully commenced in January 2021 The University approved the JSS efforts as compulsory courses to be offered to all Doctoral candidates in the University and this would be coordinated by the Postgraduate College of the University. | Prof. Sunday Adedini
5 | University of Ibadan | Institutionalization of CARTA's Joint Advanced Seminars into the Curriculum of Doctoral Training at the University of Ibadan, Nigeria. | Project Team meet to plan for the year ,Stakeholder workshops to Develop and review new curriculum , PGC curriculum committee for final review and approval of the new curriculum ,PGC Board for approval of the new curriculum, UI Senate approval of the new curriculum to the University senate , Sensitization of the academic community of the newly approved curriculum ,Evaluation/Report writing | 2019-09-01 | 2020-08-11 | [6 empty] | 2020-08-31 | 9988 | Active |  | Developed the new UI curriculum template by adapting the CARTA JAS curricula and resources to meet the requirements of each faculty/ institute/ centre at the UI (The templates was shared among members of the curriculum development team prior to the workshop). The PG College curriculum committee reviewed the UI doctoral training curriculum by adapting CARTA JAS 1-4 curriculum and integrating it as required courses with credit units |  | Could this be for UNIMA? - No it is not
6 | University of Ibadan | Enhancing Research Skills of Doctoral Students and Faculty Members in Literature Searching and Reference Management at the University of Ibadan, Nigeria | Holding Project Team meetings, developing Training Materials,holding Stakeholders meetings, training of librarian and faculty members on use of materials,training of librarian and faculty members on use of materials ,Knowledge dissemination and Second phase planning | 2018-11-01 | 2019-07-01 | 2020-08-11 |  |  |  |  | 2020-10-30 | 2019-10-31 | 9985 | Completed | 2020-10-30 |  | Prof. Akinyika Omigbodun
7 | University of Nairobi | Strengthening Capacity for doctoral supervision at University of Nairobi: PHD Students Supervisors’ Mentorship Program. | Inception Meeting, Customization of Supervisors Curricula to the institution,Training of Trainers (Deans and Directors), Training of Trainers (Chairpersons) and Training of First Batch of PhD Supervisors | 2019-09-01 | [7 empty] | 2020-08-31 | 10000 | Active |  |  | Dr. Anne Khasakhala
8 | University of the Witwatersrand | Knowledge Management and Impact Optimization of CARTA supported Research Evidence |  | 2020-10-01 | [7 empty] | 2021-04-15 | 54191 | Active |  |  | Prof. Jude Igumbor
9 | University of Rwanda | Optimization of CARTA supported Research Evidence | Institutional adaption of the Pre-doctoral research methodology course from content of the CARTA Joint Advanced Seminars (JAS). | 2017-06-28 | 2018-09-01 | 2019-03-01 | 2019-08-01 |  |  |  | 2019-11-11 | 2019-06-27 | 79320 | Completed | 2019-11-15 | Approval was granted by Senate to make teaching of research methodology compulsory. This resulted in a process of the Center for Postgraduate Studies reviewing the rules and regulations governing postgraduate studies; Content for the multi-disciplinary research method course was finalized, in collaboration with the Directorate of the UR Center for Postgraduate Studies, in March 2019, and is awaiting external review in April 2019 and approval by the University | Dr. François Niragire
10 | University of Malawi | Adaption of the CARTA curriculum, through the university approval system, as a substantive requirement for doctoral programs in the health and population sciences. |  | 2018-11-01 | [6 empty] | 2020-10-01 | 2019-10-31 | 10000 | Terminated | 2020-04-01 |  | Prof. Adamson Muula
11 | University of Nairobi | Enhancing the capacity of PhD students and Early Career Researchers on Grant proposal writing |  | 2024-01-23 | [7 empty] | 2025-01-15 | 17394.37 |  |  |  | Angeline Chepchirchir
14 | University of Ibadan | Ibadan Doctoral Academy: Competence enhancement programme for doctoral students and supervisors |  | 2024-01-24 | 2024-07-15 | 2024-10-15 | [5 empty] | 2025-01-15 | 19471.96 |  |  |  | Akinyinka/Funke
15 | Moi University | Moi University Institutionalization of the Graduate Grant Writing Workshop Project |  | 2024-03-05 | 2024-06-15 | 2024-09-15 | 2025-01-15 |  |  |  | 2025-01-15 | 2025-01-15 | 19090 |  |  |  | Christpher Odhiambo
16 | Obafemi Awolowo University | Advancing Evidence Synthesis Mastery among Early-Career Researchers at the Obafemi Awolowo University, Nigeria |  | 2024-03-05 | 2024-06-15 | 2024-09-15 |  |  |  |  | 2025-01-15 | 2025-01-15 | 19968 |  |  |  | Melvin Ojo
17 | University of Rwanda | Expanding the Institution Capacity Strengthening for Enhanced Doctoral Research Training at University of Rwanda (ECASERT) |  | 2024-08-12 | 2025-11-15 | 2025-01-15 |  |  |  |  | 2025-03-31 | 2025-03-31 | 19997 |  |  |  | Prof. Niragire
18 | Makerere University | Building the Capacity of Doctoral Students in Scholarly Writing through a Sustainable Online Training Approach. |  |  | 2024-11-15 | 2025-01-15 |  |  |  |  | 2025-04-30 | 2025-04-30 | 20000 |  |  |  | Charles Kato
19 | Makerere University | Institutionalization of Graduate Grant-Writing Workshop (GGWW) and Academic Professional and Administrative Staff (APAS) Workshop at the University of Ibadan | To institutionalize a Graduate Grant-Writing Workshop curriculum as an exit program of the Postgraduate College of the University of Ibadan. To institutionalize APAS and facilitate its adoption as part of required training for newly employed staff for them to value contributions made by various role players towards supporting PhD students. | 2024-08-17 | 2025-11-15 | 2025-01-15 |  |  |  |  | 2025-03-31 | 2025-03-31 | 19283.4 |  |  |  | Akinyinka/Funke | The University of Ibadan organized Graduate Grant-Writing Workshops (GGWW) for 101 PhD graduates of the 2024 cohort in two batches: Oct 22–24 (49 participants) and Oct 29–31 (52 participants). Using the Nairobi ToT model and CARTA curriculum, the workshops covered key themes, including grant proposal writing, budgeting, engaging funders, the peer review process, and the value of mentors, partners, and networks in grant-making. The methodology featured hands-on practical sessions, group activities, and facilitator feedback, with participants encouraged to apply for active grant calls. These workshops enhanced the grant-writing skills of participants and facilitated knowledge transfer to other institutions, where many graduates serve as lecturers and researchers. A key success was the adoption of the UI-GGWW as an exit workshop by the Board of the Postgraduate College, registered under the UI Doctoral Academy Training. | 2024-11-22
20 | Obafemi Awolowo University | Enhancing Doctoral Supervision Capacity at the Obafemi Awolowo University (EDUCATE-OAU) |  | 2024-08-12 | 2025-11-15 | 2025-01-15 |  |  |  |  | 2025-03-31 | 2025-03-31 | 19008 |  |  |  | Mapayi Boladale
21 | University of Nairobi | Faculty-based PhD supervisors training and re-tooling workshops at University of Nairobi |  | 2024-08-24 | 2025-11-15 | 2025-01-15 |  |  |  |  | 2025-03-31 | 2025-03-31 | 19924.51 |  |  |  | Rose Opiyo
22 | Kamuzu University of Health Science (KUHeS) | Strengthening research, research training, and research support systems at KUHeS and its associates |  | 2024-08-30 | 2025-11-15 | 2025-01-15 |  |  |  |  | 2025-03-31 | 2025-03-31 | 20000 |  |  |  | Fanuel Lampiao
. | Moi University | Post-Doctoral Supervision Training: Training of Trainers Based on CARTA Model at Moi University, Kenya |  | 2024-08-14 | 2025-11-15 | 2025-01-15 |  |  |  |  | 2025-03-31 | 2025-03-31 | 20000 |  |  |  | Christpher Odhiambo
24 | University of Witwatersrand | CARTA Institutionalisation at Wits: ToT workshops |  | 2024-08-30 | 2025-11-15 | 2025-01-15 |  |  |  |  | 2025-03-31 | 2025-03-31 | 19900 |  |  |  | Daphney Conco
25 | Ifakara Health Institute (IHI) | Structured postgraduate supervision program and career development and its monitoring at Ifakara Health Institute |  | 2024-10-17 | 2024-12-15 | 2025-03-15 |  |  |  |  | 2025-07-31 | 2025-07-31 | 20000 |  |  |  | Dickson Wilson

## Result summary
Re
Reporting period |  |  | February | Progress towards achieving the objective | Planned activities | No | Institution | Title of project | Objectives | Strategies | Year of Award | Activities | Outputs of activites | Challenges | Lessons Learnt | MoV Shared | Outputs | Short term outcomes | Long term outcomes | Secretariat Comment
Institution | Goal | Objectives |  |  |  | 1 | Makerere University | Strengthening capacity for doctoral training and supervision at Makerere University: a multidisciplinary doctoral students and supervisors’ mentorship approach. |  | Harmonizing of crosscutting content for the PhD curriculum; Harmonizing of Continued Professional Development (CPD) curriculum for PhD supervisors; Reviewing of graduate training policies and guidelines. | 2017-07-01 | [6 empty] | Mainstreamed the curriculum for Scholarly Writing through the incorporation of CARTA Joint Advanced Seminar (JAS) interventions. Four courses that have adopted CARTA model 1.Continued Professional Development for Doctoral supervisors. 2. Scholarly writing & Communication Skills (ART 9105) 3. Qualitative Data Analysis, Interpretation and Presentation (SOC 9101) 4) Advanced Quantitative Analysis (ISE 9106) 5) Philosophy of Method (ARTS 9102)
Makerere University | Building the Capacity of Doctoral Students in Scholarly Writing through a Sustainable Online Training Approach. | 1. Transform the already available face-to-face Scholarly Writing curriculum for virtual training. 2. Building capacity of trainers in online material development and teaching using the Makerere University MUELE virtual platform. 3. Pilot the developed Scholarly Writing virtual curriculum through training of multidisciplinary doctoral students. | The project core team held meetings with Prof. Julius Kikooma, Director of Graduate Training and Capacity Building, to discuss the structure of a scholarly training course. The key objectives were to review the course structure, assess current training modalities and gaps, and propose a team to develop an online curriculum in collaboration with CARTA. Key observations from the meetings included: Key observations from the meetings included: The Scholarly Writing and Communication Skills course is currently housed in the Department of Linguistics and Communication, though its final placement is pending. The university now has two doctoral intakes (August and April) instead of continuous admissions. The course is now a semester-long, credit-bearing module rather than a short course, integrated into the curriculum for taught PhDs and jointly offered for research-based PhDs. The DRGT is experiencing an overload of students, creating a backlog in support services. To address these challenges, it was agreed that a blended learning approach would be the most effective solution. |  | Engaging the Director of DRGT to identify academic staff from each college for the Training of Trainers (ToT) on blended delivery, who will later train a selected student cohort. The ToT is scheduled for February 24–28, 2025.Securing a venue for the ToT workshop, preferably near the Senate Building. Finalizing the design and upload of training materials onto the Muele Moodle platform. | 2 | Moi University | Improvement of Competencies and Completion Rates among Doctoral Fellows through Strengthening of Supervision, Mentorship d Integration of Courses |  | Strengthening supervisor training, supervision and mentorship process for graduate training at Moi University, Augmenting competencies of graduates by integrating and harmonizing relevant priority CARTA Joint Advanced Seminars (JASes) courses into existing graduate curricula, Institutionalizing best practices in research and grants management culture by enhancing capacity of academic and administrative staff delivery quality service and manage postgraduate training; and mobilization and management of research funds | 2019-12-01
University of Nairobi | Enhancing the capacity of PhD students and Early Career Researchers on Grant proposal writing |  |  |  |  | 3 | Moi University | Infrastructural Project on Strengthening ad Refurbishing of CARTA Postgraduate Lab/Training space; and CARTA Committee Room at Moi University (at Main Campus at School of Arts and Social Sciences) ANDICT connectivity |  |  | 2020-02-28
University of Ibadan | Institutionalization of Graduate Grant-Writing Workshop (GGWW) and Academic Professional and Administrative Staff (APAS) Workshop at the University of Ibadan |  |  |  |  | 4 | Obafemi Awolowo University | Intervention towards Strengthening Research Training in Obafemi Awolowo University (ItSTRETO) |  | Introduction of the Joint Seminars Series (JSS) and holding of Supervisors Retreats | 2017-07-01
[6 empty] | 5 | University of Ibadan | Institutionalization of CARTA's Joint Advanced Seminars into the Curriculum of Doctoral Training at the University of Ibadan, Nigeria. |  | Project Team meet to plan for the year ,Stakeholder workshops to Develop and review new curriculum , PGC curriculum committee for final review and approval of the new curriculum ,PGC Board for approval of the new curriculum, UI Senate approval of the new curriculum to the University senate , Sensitization of the academic community of the newly approved curriculum ,Evaluation/Report writing | 2019-09-01
[6 empty] | 6 | University of Ibadan | Enhancing Research Skills of Doctoral Students and Faculty Members in Literature Searching and Reference Management at the University of Ibadan, Nigeria |  | Holding Project Team meetings, developing Training Materials,holding Stakeholders meetings, training of librarian and faculty members on use of materials,training of librarian and faculty members on use of materials ,Knowledge dissemination and Second phase planning | 2018-11-01
[6 empty] | 7 | University of Nairobi | Strengthening Capacity for doctoral supervision at University of Nairobi: PHD Students Supervisors’ Mentorship Program. |  | Inception Meeting, Customization of Supervisors Curricula to the institution,Training of Trainers (Deans and Directors), Training of Trainers (Chairpersons) and Training of First Batch of PhD Supervisors | 2019-09-01
[6 empty] | 8 | University of the Witwatersrand | Knowledge Management and Impact Optimization of CARTA supported Research Evidence |  |  | 2020-10-01
[6 empty] | 9 | University of Rwanda | Optimization of CARTA supported Research Evidence |  | Institutional adaption of the Pre-doctoral research methodology course from content of the CARTA Joint Advanced Seminars (JAS). | 2017-06-28 | [5 empty] | A resesarch methodology course that adapted aspects of the CARTA including PhD training, supervision Curricula, ESEO writing among others | The course was approved by the senate on July 2020 for a harmonized delivery research course across the UR colleges
[6 empty] | 10 | University of Malawi | Adaption of the CARTA curriculum, through the university approval system, as a substantive requirement for doctoral programs in the health and population sciences. |  |  | 2018-11-01
[6 empty] | 11 | University of Nairobi | Enhancing the capacity of PhD students and Early Career Researchers on Grant proposal writing | To strengthen the grant proposal writing skills of PhD students, Early Career Researchers (ECRs), and faculty members to improve the University's research funding success. | To address the University lack of a dedicated grant-writing manual and a formal training program, which hampers researchers' ability to effectively navigate the complexities of securing research funding. | 2024-01-23 | Stakeholder engagement to gather insight, assess need and ensure buy in for the capacity building activities. Baseline needs assessment on the universities capacity for grant proposal development Training and content development workshop Recruit a cohort of PhD students and ECRs interested in grant proposal development Hold a ToT for the developed grant writing course | Completed stakeholder engagement. The engagment were through workshops, correspondence and workshop - Deans Associate deans, research Office Personnel Completed baseline survey in July 2024 indicating a lack of formal grant writing activities, and most units lacked essential reference resources. Disseminated needs assessment report Received 320 applications from for grant writing, 80 (50 faculty and 30 PhD students) were selected those who would be accomodated by the program. Organized in two cohorts Trained 51 participants on grant writing in April 2025 using the developed guide. Trained 18 ToTs in Agust 2024, training held at Masai Lod1 Training and content development workshops held to review and enhance training materials, develop comprehensive guidelines, and embed instructional design features | Low turn out for the training of 63.8%; Delayed release of second tranche of funds Low survey response rate |  | Yes- Grant writing guideline | Developed a self directed Grant writing guideline for ECRs and PhD students Trained 18 ToTs to ensure the university's sustainability and scalability of capacity-building efforts. |  |  | The project was well implemented, and the means of verification were duly shared. It would be beneficial to conduct a follow-up after some time to assess ongoing progress and evaluate the longer-term impact of the course
[6 empty] | 14 | University of Ibadan | Ibadan Doctoral Academy: Competence enhancement programme for doctoral students and supervisors |  |  | 2024-01-24
[6 empty] | 15 | Moi University | Moi University Institutionalization of the Graduate Grant Writing Workshop Project |  |  | 2024-03-05
[6 empty] | 16 | Obafemi Awolowo University | Advancing Evidence Synthesis Mastery among Early-Career Researchers at the Obafemi Awolowo University, Nigeria | Increase the proportion of ECRs at OAU that are exposed to the CARTA andragogy and academic writing curriculum Improve evidence synthesis and academic-writing skills of ECR in OAU using the CARTA curriculum; and Increase the number and quality of scientific outputs from ECR in OAU |  | 2024-03-05 | Training sessions held: Reviewing a Scoping Review Protocol, OSF Registration, and Journal Selection, Manuscript Preparation and Submission Tips Introduction to Systematic Reviews and Research Question Development Using the PICOS Framework, Refining Research Questions. Literature Searching Strategies, Refining Search Strategies, and Troubleshooting Title and Abstract Screening, Full-Text Screening, and Applying Inclusion/Exclusion Criteria and Quality Assessment | Twenty-five ECRs at Obafemi Awolowo University (OAU) have been trained in evidence synthesis, systematic review methodologies, and academic writing through structured workshops and hands-on activities. Twenty-five ECRs from different disciplines have developed scoping review protocols around five thematic areas and have them registered. |  |  | List of 24 who attended the training
[6 empty] | 17 | University of Rwanda | Expanding the Institution Capacity Strengthening for Enhanced Doctoral Research Training at University of Rwanda (ECASERT) | To foster familiarity with CARTA PhD Training materials and innovative learning approach among doctoral trainers at UR To produce co-created teaching materials for the delivery of the “multidisciplinary research methodology for doctoral studies module” borrowing from the CARTA PhD training materials. To organize the co-created teaching materials into a web-based learning module on UR E-learning platform and make them accessible for a wider use. To further collaboration between research methodology teaching stakeholders at UR to enhance the delivery and instill routine of the co-created teaching and learning materials. | Although the multidisciplinary research methodology module had been approved by the University Senate in 2020, it lacked structured and harmonized teaching and learning materials to support its effective delivery across UR colleges’ schools. With the ECASERT project support, the module delivery learning materials were co-created, peer-reviewed, and made accessible on the University of Rwanda’s ELearning platform. | 2024-08-12 | Held an awareness workshop and adjusted the project implementationplan on 09 November 2024 Designed a guiding document for the co-creation of module teaching/learning materials from 27 to 29 November 2024 Co-created a set of provisional teaching and learning materials for doctoral research methodology delivery from 10 to 13 December 2024 Reviewed the provisional teaching and learning materials and provide comments and recommendations to production of final set of materials, 07-10 February 2025 Co-created a finalised set of teaching & learning materials, 17-20 February 2025 Created and deployed the research methodology module on UR E-learning platform and with co-created teaching & learning materials, 24-25 February 2025 | The team developed a guiding document to support the co-creation of research methodology teaching and learning materials. They created and reviewed provisional content collaboratively, integrating feedback and recommendations to enhance its quality. They uploaded the finalized materials to the University of Rwanda’s E-learning platform on 24–25 February 2025. They created awareness and promoted use of the resources, they held an awareness workshop on 24 April 2025. During the session, they introduced participants to the co-created materials, the CARTA PhD training curriculum, pedagogy, and theory of change, and guided them on how to access and navigate the materials on the E-learning platform. |  |  |  |  | The co-creation exercise has been a good learning opportunity and experience for the availability of the materials, enhanced familiarity with the curriculum content, improved skills in course management on the UR ELearning platform and the discovery of open educational resources Cocreated with faculty at UR set of teaching and learning materials available on the UR learning platform in February 2025 and created awareness of the availability of the materials in April 2025 |  | The project was well imolemented and the goal to develop elearning materials achieved with the learning and teaching materials available at the UR E-learning platform. Action: Follow up with FP on MOV for the elearning course
[6 empty] | 18 | Makerere University | Building the Capacity of Doctoral Students in Scholarly Writing through a Sustainable Online Training Approach. | Transform the already available face-to-face Scholarly Writing curriculum for virtual training. Building capacity of trainers in online material development and teaching using the Makerere University MUELE virtual platform. Pilot the developed Scholarly Writing virtual curriculum through training of multidisciplinary doctoral students. |  |  | The team met Prof. Julius Kikooma, the Director Graduate Training and Capacity Building to 1. To discuss the proposed structure for the scholarly training course To discuss current training modalities and gaps To propose a team to draft an online curriculum and engage with the CARTA team. Transform the scholarly writing and communication course to virtual curriculum | That the Scholarly Writing and Communication Skills course is now housed at the Department of Linguistics and Communication, however, they have been a proposal to divide the department and the DRGT is waiting to confirm the housing unit for the course. ✓ That the university now has two intakes for doctoral students, the August and April intakes. Previously admissions were made throughout the year, especially for researchbased PhDs. ✓ That the course is no longer taken as a short course but it now runs through the entire semester and has been given credits. For taught PhDs, the course is embedded within the curriculum, and for PhDs by research, the students offer the course together. ✓ That the DRGT is grappling with an overload and a backlog of students that the department and DRGT can support.
[6 empty] | 19 | University of Ibadan | Institutionalization of Graduate Grant-Writing Workshop (GGWW) and Academic Professional and Administrative Staff (APAS) Workshop at the University of Ibadan |  | To institutionalize a Graduate Grant-Writing Workshop curriculum as an exit program of the Postgraduate College of the University of Ibadan. To institutionalize APAS and facilitate its adoption as part of required training for newly employed staff for them to value contributions made by various role players towards supporting PhD students. | 2024-08-17
[6 empty] | 20 | Obafemi Awolowo University | Enhancing Doctoral Supervision Capacity at the Obafemi Awolowo University (EDUCATE-OAU) | Co-create and adapt CARTA’s doctoral supervisory curriculum at OAU. Expose 2 cohorts of doctoral supervisors to the CARTA supervisors’ curriculum using experiential learning and communities of practice. Initiate real-time online monitoring of supervision performance to enhance the quality of the supervisor-supervisee relationship. Explore the perception of the supervisors and supervisees on the CARTA-OAU supervisors’ curriculum. |  | 2024-08-12 | Brainstorming
[6 empty] | 21 | University of Nairobi | Faculty-based PhD supervisors training and re-tooling workshops at University of Nairobi |  |  | 2024-08-24
[6 empty] | 22 | Kamuzu University of Health Science (KUHeS) | Strengthening research, research training, and research support systems at KUHeS and its associates |  |  | 2024-08-30 | Held academic wriitng workshop between 2-4 April for postgraduate students at Malawi University of Science and Technology. The workshop brought together 50 MSc, and PhD students who were equiped with skills in manuscript writing. Facilitators Prof David Mkwambisi – MUST Prof Andrew Mtewa – MUST Prof Fanuel Lampiao – KUHeS Dr Anthony Mwakikunga - KUHeS | Participants were imparted skills on how to write a manuscript for publication. II. Participants were oriented on which journals to target for publishing their manuscripts III. Participants learned about the ethical use of AI in publishing. IV. Networking opportunity; participants left the meeting with a renewed interest in collaborating with other students from different fields | Participants were at different stages in their MSc and PhD journey therefore special attention was required to meet the needs of all. Some participants had no data so did not benefit from the practical part of the workshop. | There is need for the universities in Malawi to periodically conduct these workshop so that students are given skills on how to write manuscripts for publication |  | 50 students trained on manuscript writing
[6 empty] | . | Moi University | Post-Doctoral Supervision Training: Training of Trainers Based on CARTA Model at Moi University, Kenya |  |  | 2024-08-14
[6 empty] | 24 | University of Witwatersrand | CARTA Institutionalisation at Wits: ToT workshops |  |  | 2024-08-30
[6 empty] | 25 | Ifakara Health Institute (IHI) | Structured postgraduate supervision program and career development and its monitoring at Ifakara Health Institute |  |  | 2024-10-17 | [5 empty] | manuscripts.

## Sheet2
No | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | . | 24 | 25
Institution | Makerere University | Moi University | Moi University | Obafemi Awolowo University | University of Ibadan | University of Ibadan | University of Nairobi | University of the Witwatersrand | University of Rwanda | University of Malawi | University of Nairobi | University of Ibadan | Moi University | Obafemi Awolowo University | University of Rwanda | Makerere University | University of Ibadan | Obafemi Awolowo University | University of Nairobi | Kamuzu University of Health Science (KUHeS) | Moi University | University of Witwatersrand | Ifakara Health Institute (IHI)
Year of Award | 2017-07-01 | 2019-12-01 | 2020-02-28 | 2017-07-01 | 2019-09-01 | 2018-11-01 | 2019-09-01 | 2020-10-01 | 2017-06-28 | 2018-11-01 | 2024-01-23 | 2024-01-24 | 2024-03-05 | 2024-03-05 | 2024-08-12 |  | 2024-08-17 | 2024-08-12 | 2024-08-24 | 2024-08-30 | 2024-08-14 | 2024-08-30 | 2024-10-17
Title of project | Strengthening capacity for doctoral training and supervision at Makerere University: a multidisciplinary doctoral students and supervisors’ mentorship approach. | Improvement of Competencies and Completion Rates among Doctoral Fellows through Strengthening of Supervision, Mentorship d Integration of Courses | Infrastructural Project on Strengthening ad Refurbishing of CARTA Postgraduate Lab/Training space; and CARTA Committee Room at Moi University (at Main Campus at School of Arts and Social Sciences) ANDICT connectivity | Intervention towards Strengthening Research Training in Obafemi Awolowo University (ItSTRETO) | Institutionalization of CARTA's Joint Advanced Seminars into the Curriculum of Doctoral Training at the University of Ibadan, Nigeria. | Enhancing Research Skills of Doctoral Students and Faculty Members in Literature Searching and Reference Management at the University of Ibadan, Nigeria | Strengthening Capacity for doctoral supervision at University of Nairobi: PHD Students Supervisors’ Mentorship Program. | Knowledge Management and Impact Optimization of CARTA supported Research Evidence | Optimization of CARTA supported Research Evidence | Adaption of the CARTA curriculum, through the university approval system, as a substantive requirement for doctoral programs in the health and population sciences. | Enhancing the capacity of PhD students and Early Career Researchers on Grant proposal writing | Ibadan Doctoral Academy: Competence enhancement programme for doctoral students and supervisors | Moi University Institutionalization of the Graduate Grant Writing Workshop Project | Advancing Evidence Synthesis and Academic Writing Mastery Skills among Early-Career Researchers at the Obafemi Awolowo University, Nigeria | Expanding the Institution Capacity Strengthening for Enhanced Doctoral Research Training at University of Rwanda (ECASERT) | Building the Capacity of Doctoral Students in Scholarly Writing through a Sustainable Online Training Approach. | Institutionalization of Graduate Grant-Writing Workshop (GGWW) and Academic Professional and Administrative Staff (APAS) Workshop at the University of Ibadan | Enhancing Doctoral Supervision Capacity at the Obafemi Awolowo University (EDUCATE-OAU) | Faculty-based PhD supervisors training and re-tooling workshops at University of Nairobi | Strengthening research, research training, and research support systems at KUHeS and its associates | Post-Doctoral Supervision Training: Training of Trainers Based on CARTA Model at Moi University, Kenya | CARTA Institutionalisation at Wits: ToT workshops | Structured postgraduate supervision program and career development and its monitoring at Ifakara Health Institute
Objectives | [13 empty] | Increase the proportion of ECRs at OAU that are exposed to the CARTA andragogy and academic writing curriculum Improve evidence synthesis and academic-writing skills of ECR in OAU using the CARTA curriculum Increase the number and quality of scientific outputs from ECR in OAU |  | Transform the already available face-to-face Scholarly Writing curriculum for virtual training. Building capacity of trainers in online material development and teaching using the Makerere University MUELE virtual platform. Pilot the developed Scholarly Writing virtual curriculum through training of multidisciplinary doctoral students. |  |  |  | The project aims to upscale the institutionalization of the CARTA interventions at the KUHeS and its associate universities in Malawi namely, the UNIMA, MUST, and MUBAS.
Strategies | Harmonizing of crosscutting content for the PhD curriculum; Harmonizing of Continued Professional Development (CPD) curriculum for PhD supervisors; Reviewing of graduate training policies and guidelines. | Strengthening supervisor training, supervision and mentorship process for graduate training at Moi University, Augmenting competencies of graduates by integrating and harmonizing relevant priority CARTA Joint Advanced Seminars (JASes) courses into existing graduate curricula, Institutionalizing best practices in research and grants management culture by enhancing capacity of academic and administrative staff delivery quality service and manage postgraduate training; and mobilization and management of research funds |  | Introduction of the Joint Seminars Series (JSS) and holding of Supervisors Retreats | Project Team meet to plan for the year ,Stakeholder workshops to Develop and review new curriculum , PGC curriculum committee for final review and approval of the new curriculum ,PGC Board for approval of the new curriculum, UI Senate approval of the new curriculum to the University senate , Sensitization of the academic community of the newly approved curriculum ,Evaluation/Report writing | Holding Project Team meetings, developing Training Materials,holding Stakeholders meetings, training of librarian and faculty members on use of materials,training of librarian and faculty members on use of materials ,Knowledge dissemination and Second phase planning | Inception Meeting, Customization of Supervisors Curricula to the institution,Training of Trainers (Deans and Directors), Training of Trainers (Chairpersons) and Training of First Batch of PhD Supervisors |  | Institutional adaption of the Pre-doctoral research methodology course from content of the CARTA Joint Advanced Seminars (JAS). | [7 empty] | To institutionalize a Graduate Grant-Writing Workshop curriculum as an exit program of the Postgraduate College of the University of Ibadan. To institutionalize APAS and facilitate its adoption as part of required training for newly employed staff for them to value contributions made by various role players towards supporting PhD students. |  |  | 1. Conduct a workshop with faculty deans, heads of departments, and administrators involved in postgraduate student enrollment at each university enlightening them about the CARTA practices. Conduct trainer of trainer’s postgraduate supervision workshops for faculty members involved in student supervision to gain skills on how best to supervise using the CARTA curriculum Conduct academic writing workshops for postgraduate students aimed at strengthening their skills in manuscript writing
Long term outcomes
Short term outcomes | [16 empty] | APAS participants have expressed a strong commitment to supporting research training and advancing the institutional agenda. Their renewed understanding of the uniqueness of their roles and the importance of leadership synergy is expected to contribute significantly to enhancing research excellence at the University. Two participants of the Graduate workshop secured Postdoc positions on the NIHR project at the University of Ibadan Graduate Grant-Writing Workshop curriculum materials has been institutionalised as an exit workshop in the doctoral academy at the Postgraduate College of University of Ibadan Adoption of APAS curriculum as part of entry-level training for new staff at the University by the Directorate of Career Development and Counselling Centre
Outputs | Increased awareness among faculty members of the associate universities regarding carta practices. The session provided an opportunity to demistify misconception about the program; for instance, other participants misinterpreted the objectives of CARTA, thinking it is only for certain types of research and courses, others thought it is only available to specific countries, leading to disengagement or reluctance to participate | [12 empty] | ECRs developed stronger competencies in systematic and scoping reviews, including protocol development, literature search strategies, and research question formulation using the PICOS framework. Twenty-five ECRs from different disciplines have developed scoping review protocols around five thematic areas and have them registered. Development of Protocols for systematic reviews is also ongoing across five thematic research areas. The use of an Open Science Framework (OSF) for protocol registration promotes transparency and reproducibility in research, aligning OAU’s research outputs with global best practices. Training on PRISMA compliance and data documentation strengthens OAU’s capacity for high-impact, policy-relevant research. Increased networking and collaboration among ECRs and facilitators: This is yielding some positive results through interdisciplinary collaborations among ECRs and senior academics on scoping reviews and systematic reviews. |  |  | As part of the mentorship initiative during the intergenerational collaborations, research training GGWW workshop, graduates were paired with experts programs) in their field who comprehensively reviewed their submitted grant research proposals. APAS participants have expressed a strong commitment to supporting research training and advancing the institutional agenda. Their renewed understanding of the uniqueness of their roles and the importance of leadership synergy is expected to contribute significantly to enhancing research excellence at the University.
Activities | [13 empty] | Twenty-five ECRs at Obafemi Awolowo University (OAU) have been trained in evidence synthesis, systematic review methodologies, and academic writing through structured workshops and hands-on activities. |  | The team met Prof. Julius Kikooma, the Director Graduate Training and Capacity Building to 1. To discuss the proposed structure for the scholarly training course To discuss current training modalities and gaps To propose a team to draft an online curriculum and engage with the CARTA team. Transform the scholarly writing and communication course to virtual curriculum Development and uploading of online training materials to the Makerere learning platform is ongoing. A course shell has been created. The core team held a meeting between the , the Director DRGT, and the head of the Department of English Language, Communication Skills, which houses the Scholarly Writing and Communication course, they discussed teh modalities and logistics and timelines of the course. They will organize a ToT for faculty from each college offering the course. online |  |  |  | Held sensitization meetings with faculty deans, heads of departments, and administrators involved in postgraduate student enrollment at each university (MUST, MUBAS, UNIMA, and KUHeS) enlightening them about the CARTA practices from the 4th of November to the 14th of November 2024.
That the Scholarly Writing and Communication Skills course is now housed at the Department of Linguistics and Communication, however, they have been a proposal to divide the department and the DRGT is waiting to confirm the housing unit for the course. ✓ That the university now has two intakes for doctoral students, the August and April intakes. Previously admissions were made throughout the year, especially for researchbased PhDs. ✓ That the course is no longer taken as a short course but it now runs through the entire semester and has been given credits. For taught PhDs, the course is embedded within the curriculum, and for PhDs by research, the students offer the course together. ✓ That the DRGT is grappling with an overload and a backlog of students that the department and DRGT can support.
Way forward | [15 empty] | Contact through the Director DRGT representatives of academic staff from each college to participate in the TOT training for blended delivery and subsequently train a selected cohort of students. Dates for the TOT were confirmed as 24-28 February 2025. ➢ Secure the venue for the ToT workshop i.e., around Senate Building ➢ Finalize the design and upload of training materials onto the Muele Moodle platform.

## List
Completion status
Active
Terminated
Completed